SURVIVAL IN PIXEL

Development & Steam Launch Planning Guide

A time-travel survival RPG built in Java + LibGDX

| Field | Detail |
| --- | --- |
| Genre | Survival RPG (2D, top-down) |
| Engine / Stack | Java 21 LTS, LibGDX, Gradle, IntelliJ IDEA |
| Platform (initial) | Windows (Steam) |
| Premise | The player time-travels to the past and must survive from a hut while searching for a way home |
| Core pillars | Survival systems, RPG progression, action-based skills/powers |

# How This Guide Is Organized

This guide covers the full path from an empty Gradle project to a live Steam store page, in the order you'll actually do the work. There are two tracks that run in parallel for most of development:

- Game development track — building the game itself, phase by phase.

- Steam publishing track — everything Valve requires, which should start months before you plan to launch, not after the game is finished.

Treat the phase numbers as milestones, not fixed deadlines — a solo/small-team project should expect each phase to take longer than it feels like it should.

# Part 1 — Game Development Roadmap

## Phase 0: Pre-Production (1–2 weeks)

Before writing gameplay code, lock down the foundation so you're not redesigning systems mid-build.

- Write a one-page design doc: core loop, win condition ("find a way back"), and the 4–6 systems that support it

- Decide the time-travel hook concretely — is the player's era-knowledge the source of their skills, or does the past world itself grant powers? This decision shapes the whole skill tree.

- Sketch the hut as home base: what it does mechanically (save point, crafting, storage, upgrades)

- Set up the project skeleton: Java 21 + LibGDX + Gradle + IntelliJ, folder structure (core/player/world/enemies/combat/items/UI/assets)

- Set up Git + a GitHub repo from day one — commit early, commit often

- Pick your art style and tile size now (pixel art at a fixed resolution, e.g. 16x16 or 32x32) — changing this later means redoing every asset

## Phase 1: Prototype (2–4 weeks)

Goal: prove the core loop works before investing in content. Keep the map tiny.

- Player movement + camera following the player

- Collision with terrain/objects

- One small hand-built map in Tiled, centered on the hut

- One basic enemy with simple AI (chase/attack)

- Player health + one weapon + hit detection

- Walk out from the hut, fight, walk back — if this loop isn't fun yet, fix it before adding more systems

## Phase 2: Survival Systems (3–5 weeks)

- Hunger, thirst, stamina meters that drain over time

- Day/night cycle

- Food and water sources, basic cooking/crafting at the hut

- System interactions (e.g. low hunger → slower movement → harder combat) so survival stats actually matter in combat

- Hut upgrades tied to survival needs (storage, bed, water collection)

## Phase 3: RPG Progression (3–5 weeks)

- XP and leveling

- Stats: Strength, Agility, Endurance, Intelligence, Survival (or your own set)

- Skill tree for the action skills/powers — tie unlocks to story beats (each step toward "home" grants a new ability)

- Equipment and inventory UI

- Balance pass: does progression feel earned, not just numeric?

## Phase 4: World & Content (4–8 weeks, ongoing)

- Expand the map — additional biomes/areas between the hut and the "way home"

- NPCs and any dialogue/quest system

- Multiple enemy types with distinct behavior, not just palette swaps

- Loot tables, weather, additional buildings

- Main quest structure: fragments/relics/portal pieces that gate progress and tie into the ending

## Phase 5: Polish (3–6 weeks)

- Music, sound effects, ambience (Audacity + sourced/created assets)

- Animations and particle effects

- UI/UX pass — readability, controller support if desired

- Save/load system

- Settings menu (audio, key rebinding, resolution)

- Performance profiling and optimization

- Full playtest pass with people outside the project

# Part 2 — Steam Publishing Roadmap

Start this track roughly 2–6 months before your target launch date — store page setup, wishlists, and Valve's review all take real calendar time. It overlaps with Phase 3–5 of development, not just the end.

## Cost & Timeline Summary

| Item | Detail |
| --- | --- |
| Steam Direct fee | $100 per game (one-time, recoupable after the game earns $1,000 in revenue) |
| Valve's revenue cut | 30% up to $10M, 25% from $10M–$50M, 20% beyond that |
| Build review time | Roughly 1–5 business days per submitted build |
| Identity/tax verification | A few days to ~1 week |
| Recommended wishlist run-up | 2–6 months before launch, via a public store page |

## Step 1 — Create a Steamworks Account

- Create/use a regular Steam account, then sign in at partner.steamgames.com

- Pay the $100 USD Steam Direct fee (charged per game/app you publish)

- Complete tax interview (W-9 for US, W-8BEN for international individuals, W-8BEN-E for entities)

- Add bank account details for payouts; confirm your country supports direct deposit, or plan for wire/PayPal

- Wait for identity verification — do this early, it's a common bottleneck

## Step 2 — Set Up Your App on Steamworks

- Create a new App entry for Survival in Pixel

- Fill in basic app info: title, type (Game), supported platform (Windows to start)

- Decide on DRM approach (Steam's default DRM is optional and free)

- If using achievements, Steam Cloud saves, or trading cards, configure these in Steamworks — plan them into Phase 5 of development

## Step 3 — Build Your Store Page

- Game description (short + long), key features, genre tags

- Capsule art (small/main/header images) — budget time or money for this, it drives click-through

- Screenshots (5+ recommended) showing the hut, combat, and skills in action

- A gameplay trailer (30–60 seconds is typical) — even a rough one is better than none for early wishlist building

- Set the page live in "Coming Soon" state as early as reasonably possible to start collecting wishlists

- System requirements (minimum/recommended) once you have a testable build

## Step 4 — Packaging the Build

- Package your LibGDX project as a Windows executable (a bundled JRE via jpackage/jlink is the common approach so players don't need Java installed)

- Test the packaged build on a clean Windows machine/VM, not just your dev machine

- Install and configure SteamPipe (Valve's build/upload tool) via the Steamworks SDK

- Define your Depot(s) and Build scripts (.vdf files) describing what files ship

- Upload a build, assign it to a branch (start with an internal/beta branch, not "default", for testing)

## Step 5 — Steam Integration (Optional but Common)

- Steamworks SDK integration for achievements, cloud saves, or rich presence, if you want them at launch

- Controller configuration (Steam Input) if you support controllers

- Test everything on the beta branch with a small group before promoting to default

## Step 6 — Pricing & Regional Settings

- Set your base (USD) price — Valve auto-generates regional pricing, review and adjust for major markets

- Decide on a launch discount if desired (common for wishlist conversion)

- Confirm your revenue split understanding: 70% to you up to $10M in that game's lifetime revenue

## Step 7 — Submit for Review

- Complete Steam's content survey (violence, mature content, etc.) — this affects age gating and store visibility

- Submit your default-branch build and store page for Valve's review

- Expect roughly 1–5 business days for review; address any flagged issues and resubmit if needed

## Step 8 — Launch

- Set your release date once the build and store page are approved

- Prepare launch-day materials: announcement post, trailer, press/streamer outreach if applicable

- Promote the build to your default (live) branch at launch time

- Monitor Steamworks analytics and player reviews closely in the first 48–72 hours for critical bugs

## Step 9 — Post-Launch

- Patch quickly for launch-week bugs — this is normal, not a sign something went wrong

- Keep the store page fresh with updates, screenshots, and community posts

- Consider post-launch content (new areas, skills, or a DLC) once the core game is stable

# Suggested Combined Timeline

| Development Milestone | Parallel Steam Task |
| --- | --- |
| Phase 0–1: Pre-production & Prototype | Create Steamworks account, pay Direct fee, start tax/bank verification |
| Phase 2: Survival systems | Draft store page copy, start concept art for capsule images |
| Phase 3: RPG progression | Take early screenshots, rough out a teaser trailer |
| Phase 4: World & content | Publish store page as "Coming Soon", begin wishlist push |
| Phase 5: Polish | Package Windows build, set up SteamPipe, test on beta branch |
| Launch prep | Submit build + store page for review, set release date |
| Post-launch | Patch, update store page, plan next content |

This is a planning skeleton, not a fixed schedule — adjust phase lengths to your actual pace, and start the Steamworks account/tax verification step early since it has the longest external wait time of anything in this guide.